## START HERE
TAPESTRY SMOKE TESTING
One living workbook. Your Pass/Fail marks are saved - reopen this file anytime and pick up where you left off. Every new test plan becomes a new tab here.
Tab | Needs you | What it is
Full Smoke 2026-07-13 | 9 items | 40/49 already passed. 4 quick confirms (fixed in code since) + 5 real unknowns.
New Fixes 2026-07-13 | 23 items | None run yet. Communities, economy, env-damage, strangers-proofing. 1 browser.
Mechanics Verify 2026-07-06 | 15 items | None run yet. The owed live-verifies. Needs 2 browsers (GM + player).
Portrait Bank 2026-08-03 | 5 items | None run yet. UI click-through insurance for the private-portrait-bucket fix (already storage-layer verified). Not blocking.
Onboarding Tour 2026-08-04 | 5 items | None run yet. LOCALHOST ONLY (dev server). Arrow-pointer + drag polish on the new-player tour, held uncommitted pending your look.
FASTEST PATH
1. Full Smoke tab: the 9 open items sit at the TOP (amber = quick confirm, red = real unknown). Everything below the grey divider already passed - ignore it.
2. New Fixes + Mechanics tabs: every row needs you; work top to bottom.
3. Mark the Result column (dropdown) as you go. Amber/red/blue rows = action; grey rows = done.
4. Tip: click the filter arrow on 'Status' to show only what you want (e.g. hide DONE).

## Full Smoke 2026-07-13
Item | Status | Description / what to do | Result | Notes
RESUME HERE - only these 9 need you. Everything below the grey divider already PASSED (kept for reference, no action). Amber = quick confirm (a fix shipped since your last run). Red = real unknown, report carefully.
QUICK CONFIRMS - a fix shipped since you last ran these; just verify they now pass
6b | RE-TEST | Open a generated NPC's card and find its weapon ammo. Expected: NPC starts SCARCE (0-5 loaded; full = wrong). What does its loaded ammo show? --> Was FAIL ('doesn't show anywhere'); NpcCard now shows an amber loaded/clip chip (shipped). Expect: visible now. | Pass | (prev: FAIL - doesn't show anywhere)
10 | RE-TEST | Make it the NPC's turn; have the NPC Attack your PC and fire a few times. --> Was FAIL ('can't find this'); the NPC's Attack IS the sword button on its own card. Expect: findable now. | Pass | (prev: FAIL - can't find it)
10a | RE-TEST | Did the NPC's OWN ammo go down each shot (not stay full forever)? (yes/no) --> Was 'can't tell'; NPC ammo now displays on the card. Expect: drops each shot. | went don't | could not reload via READY WEAPON (see recording)
14b | RE-TEST | Sickness drops a PC to 0 WP: did a Stress pip get added at the same time? (check stress before vs after) --> Was incomplete; the WP->0 stress pip was hardened (H10). Expect: +1 pip. | Incomplete | unable to load the NPC's machete and mke a player sick
REAL UNKNOWNS - the two chronic owed items; report exactly what you see
11 | OWED | On your PC's turn take a shot; with Insight Dice available, use the green Spend Insight Dice to reroll a die and land another hit. | Pass
11a | OWED | After the reroll, did the NPC's WP drop only ONCE more (the reroll's damage), or take TWO hits' worth? Note WP before reroll + after. | unsure | see recording
11b | OWED | Expected: the reroll REPLACES the first result - only the final roll's damage counts, not original + reroll. Did that hold? (yes/no) --> CHRONIC OWED item - real unknown. | unsure | see recording
20 | OWED | (Needs a vehicle) Open the vehicle popout in window 1; toggle a mounted weapon's firing arc. | Pass
20a | OWED | Did the change reflect in the OTHER window / on the map with no refresh? (yes/no) --> CHRONIC OWED item - real unknown. | yes
------------------------------ ALREADY PASSED / N-A - reference only, NO ACTION ------------------------------
PART A - Setup + starting loadout (one browser, you = GM)
1 | DONE | Log in as your GM/Thriver account and reach your dashboard. | Pass
1a | DONE | Sidebar visible? (yes/no) | Pass
2 | DONE | Sidebar -> Random Character. Save/keep the character it rolls. | Pass | Caius Blaine
2a | DONE | Did it create a character with a name + a RANGED weapon (pistol/rifle)? (note the name + the weapon) | Pass | Light Pistol says "Primary Ammo (Relods) 6" - that feels too many?
2b | DONE | Open the sheet/card; find the weapon ammo + the Clips (reloads) control. What does the clip show (e.g. 6/6) and how many reload pips are filled? (write both) | Pass | 6 Ammo, 6 Reloads = 36 bullets (this is wrong)
2c | DONE | Expected: FULL clip + 1 to 6 reload pips. Is the clip full and reloads in 1-6? (yes/no + numbers) | yes | 6 Ammo, 6 Reloads = 36 bullets (this is wrong)
3 | DONE | Click Reload a few times in a row. | Pass
3a | DONE | Does the clip refill and the reload count go DOWN by one each time? (yes/no) | yes
3b | DONE | Keep clicking Reload past zero reloads. Does the button stop / grey out, or reload forever? (which) | Pass | Stops
4 | DONE | Sidebar -> My Stories -> create a new Story; add your character as your survivor. | Pass
4a | DONE | Did the character appear in the party/roster? (yes/no) | Yes
PART B - Combat correctness (same browser)
5 | DONE | Launch the Table, then start a session (dice/combat unlock). | Pass
5a | DONE | Session controls unlocked? (yes/no) | Yes
6 | DONE | Open the NPC tools, generate ONE NPC with a ranged weapon, place it on the map. | Done
6a | DONE | Did an NPC appear? (note its name) | Yes | Palmer Price
7 | DONE | Start combat (Into the Moment), roll initiative. | Yes
7a | DONE | Turn bar shows your PC + the NPC? (yes/no) | Yes
8 | DONE | On your PC's turn, Attack the NPC with your ranged weapon; complete the roll (aim to hit). | Done
8a | DONE | Did the NPC's WP drop by a sensible amount? (number) | yes
8b | DONE | Check your PC's ammo. Did firing use exactly ONE round (or the burst count)? (yes/no + new ammo) | yes | 5/6
9 | DONE | Take another shot at the NPC but aim to MISS (or fire with no valid target). | Done
9a | DONE | Did your ammo go DOWN even though it missed / had no target? (yes/no) [Expected: yes] | yes
10b | DONE | Did your PC's ammo stay untouched by the NPC's shots? (yes/no) | yes
12 | DONE | Do an Upkeep check on a weapon in Pristine condition and roll well (Wild Success / a great roll). | partial pass | did this on a weapon in (Used) condition and it worked
12a | DONE | Did the weapon STAY Pristine (not drop to Used)? (yes/no) [Expected: yes] | partial pass | see 12a
PART C - Rest, sickness, clock (same browser)
13 | DONE | End combat. Note the in-game date/clock (day + hour). | done
13a | DONE | Wrote down the day + hour? (write it) | done | Campaign Day 4 · 12 AM, March 5th, Year 0
14 | DONE | Apply an infection/sickness to your PC (GM infection tools); advance the clock several days (Advance Time) until the sickness ends. | pass | this needs to move from being a browser level check to a modal
14a | DONE | Did Advance Time COMPLETE (modal closed, clock moved) rather than hang? (which) | yes | note - this infection went straight to a last ing wound. There needs to be a PHY check
15 | DONE | Apply a long Rest (24h) on your PC's card. | done
15a | DONE | Did WP/RP recover? (yes/no) | yes
15b | DONE | Note the clock after the rest (day + hour). | done | Campaign Day 7 · 12 AM, March 8th, Year 0
PART D - Two-window realtime (2nd browser as your PLAYER account, join the same Story; window 1 = GM, window 2 = player)
16 | DONE | Window 1 (GM): reveal a NEW pin to players. | pass
16a | DONE | Window 2 (player), NO refresh: did the pin appear in BOTH the map AND the right-side Pins list within ~30s? (yes/no for each) | yes
17 | DONE | Window 2: player has a character selected (its sheet/card showing). Window 1 (GM): deal damage to that character. | yes
17a | DONE | Window 2, NO refresh: did the character's WP/RP on the open card update on its own within a few seconds? (yes/no) | yes
18 | DONE | Add a SECOND player (or player leaves + rejoins). Window 1 (GM): watch the roster / party list. | yes
18a | DONE | Did the new/returning player appear on its own without you refreshing? (yes/no) | yes
19 | DONE | Window 1: move one of your tokens on the tactical map. | yes
19a | DONE | Did it move in window 2 within a couple seconds? (yes/no) | yes

## New Fixes 2026-07-13
Item | Status | Description / what to do | Result | Notes
READ FIRST - this verifies THIS SESSION's fixes (communities, economy, env-damage, strangers-proofing). The earlier combat/ammo/realtime batch is in full-smoke-testplan-2026-07-13.xlsx. Some items need a specific setup (noted). One browser unless a step says otherwise.
PART A - Communities (Gate 4)
1 | TEST | In a Story with a community/group, recruit NPCs until the group has ENOUGH combined members (party PCs + NPC members) to reach 13 - e.g. 4 PCs + 9 NPCs.
1a | TEST | Open that group and click Run Weekly Check. Does it actually ROLL now (not block with 'only N members, this is a Group')? (yes/no)
1b | TEST | Does the header show the COMBINED count, e.g. '13 members'? (write what it shows)
2 | TEST | Open the Recruit modal, leave the community dropdown on the default 'Current group', and recruit an NPC. Repeat 2-3 times on the default.
2a | TEST | Do all the recruits land in the SAME group (not a new duplicate '<Name>'s Group' each time)? (yes/no - note how many groups exist after)
3 | TEST | (Needs a community that has failed Morale twice already - optional/hard to set up) On the 3rd Morale failure, roll a SUCCESSFUL Retention Check.
3a | TEST | Did the community SURVIVE but still LOSE the failed-morale departures (some NPCs left), rather than keeping everyone? (yes/no) [test-covered; skip if no setup]
4 | TEST | Create an NPC-led or self-led group, then have the founding leader LEAVE the community.
4a | TEST | Does the leader seat clear (no dangling ex-leader; a successor picked or leaderless)? (yes/no)
PART B - Environmental damage (Gate 2 / M8)
5 | TEST | Open a character card in an active session. Look at the GM-action buttons (Reduce Stress / Env. Damage / Rest area).
5a | TEST | Is there exactly ONE 'Env. Damage' button (not two, and no separate 'Env Dmg')? (yes/no)
6 | TEST | Click Env. Damage -> Drowning. Enter a number of rounds SMALLER than 6 + the character's PHY (e.g. 3 rounds on a PHY 0 character = within the 6-round hold-breath window).
6a | TEST | Did it deal ZERO damage (within the hold-breath window), and show a 'held breath' feed row? (yes/no) [the old bug dealt rounds x 3 with no window]
6b | TEST | Now enter rounds ABOVE the window (e.g. 9). Did it deal damage AND write a feed-log row? (yes/no)
PART C - NPC ammo on the card (Gate 6 / smoke re-check)
7 | TEST | Open a generated NPC's sheet/card that has a ranged weapon.
7a | TEST | Does the weapon chip show its loaded/clip ammo (e.g. '2/6 +1 clip')? (yes/no)
7b | TEST | On an NPC with an EMPTY clip (0 loaded), is its Attack button disabled / marked EMPTY? (yes/no)
PART D - Strangers-proofing (Gate 5) - most need a 2nd (non-Thriver / observer) account
8 | TEST | (Needs a NON-Thriver test account) Sign in as a non-Thriver and go to /tools/token-creator.
8a | TEST | Are you blocked with 'This tool is Thriver-only' (NOT able to see the Bulk Upload tab)? (yes/no) [skip if no non-Thriver account]
9 | TEST | (Needs the observer flow) Join a Story as an OBSERVER (observer link), then re-join the SAME story with the NORMAL player invite/code.
9a | TEST | Are you now a normal PLAYER (can pick a survivor), not stuck as an invisible observer? (yes/no) [skip if you can't set up an observer]
10 | TEST | Try attaching an oversized (e.g. >10 MB) or non-image file to a pin via Quick Add.
10a | TEST | Is the non-image / oversized file REJECTED (not uploaded)? (yes/no) [skip if awkward to test]
Report back
Fill Pass/Fail + notes and send it back. Skip any step whose setup you can't easily do (mark 'skip') - several are error-path/edge cases already covered by unit tests; the ones that matter most for a quick pass are Parts A, B, C.

## Mechanics Verify 2026-07-06
Item | Status | Description / what to do | Result | Notes
READ FIRST - closes the ~8 owed live-verifies in one sitting. TWO browser windows on the same campaign table: GM window (you as GM) + PLAYER window (a second login that owns a PC at that table). Work top to bottom; after each block note what you saw. Table: https://thetapestry.distemperverse.com/stories/<your-campaign>/table - the 'roll feed' = the Logs panel.
Block 1 - Checks menu (no combat needed; one PC at table + one NPC revealed/on map)
1 | TEST | First Impression (PLAYER window): Checks -> First Impression. Pick a skill, pick the NPC, Roll First Impression. Do NOT click the green Spend-Insight boxes. Before rolling, count that PC's filled green Insight blocks. Roll (repeat until a 'Moment of Insight' result). Report the green-block count BEFORE and AFTER that result.
2 | TEST | Heal: Checks -> Heal. Pick a target PC, pick a kit, roll. Report the roll-feed line.
3 | TEST | Gut Instinct: Checks -> Gut Instinct, click a PC. Report the feed line.
4 | TEST | Group Check: Checks -> Group Check, run it. Report the feed line.
Block 2 - Combat (roll initiative first; GM places an armed NPC next to a PC, start combat)
5 | TEST | Disarm -> loot -> fire (PLAYER, on PC turn): action bar -> Disarm, target NPC, roll (repeat until it lands). When it lands, report what appears on the NPC's cell + its combat bar. Then take the dropped weapon from the map, Ready Weapon -> Equip from Inventory, and report whether that PC can then attack with it.
6 | TEST | Grapple (PC turn): action bar -> Grapple, target an adjacent enemy, roll. Report the feed line + whether the target shows a grappled state.
7 | TEST | Unjam / Repair (PC turn, readied weapon): open Ready Weapon. Gun -> Unjam; melee -> Repair. Click, roll. Report the feed line.
8 | TEST | End-of-combat infection: have the armed NPC wound a PC, then GM ends combat. Watch the PLAYER window: does an 'Infection Check (Wound)' roll window pop up on the player's own screen? (yes/no)
(Optional/fiddly) Broken-weapon gate: needs a weapon at Broken condition. On that PC's turn click Attack and report the message. Skip if none - unit tests cover it.
Block 3 - Vehicle popout (2 windows; GM places a vehicle token, click -> Popout)
9 | TEST | Seat propagation: in the popout, seat a crew member in the Driver seat and confirm. Watch the vehicle token in the OTHER window. Report what changed on that token (seat/passenger badge, token vanishing into the seat).
10 | TEST | Vehicle checks: in the popout run Driving, Navigate, and Brew (each needs its seat filled; Brew needs a still + supplies). Report the feed line each produces, or which button was greyed out.
Block 4 - Tactical canvas scale (2 windows; GM on a wide window, player on a narrow one)
11 | TEST | Report whether the background art lines up with the grid the same way in both windows (pick a landmark; is it on the same grid cell for both?), and whether every token sits on the art rather than in black empty space.
12 | TEST | GM: drag a corner handle to resize the background, then reload both windows. Report whether the resized art persisted and whether both windows show the same size.
Block 5 - Other surfaces
13 | TEST | Stockpile deposit (PLAYER): open the PC's Inventory, pick an item, deposit it to a community stockpile (purple community recipient). Report whether it left the inventory, and whether it shows in that community's stockpile in the OTHER window with no refresh.
14 | TEST | World-map pin: both windows open the world map. Add a pin in one. Report whether it appears in the other window on its own. (If you can't find the Add-a-Pin control, say so.)
Block 6 - Rest (anytime) - NOTE: Rest is now the GM-only PARTY REST modal (H10 fix). Expect one clock advance for the whole party, not per-PC.
15 | TEST | On the GM side click Rest, enter some hours/days, Rest Party. Report whether each PC's Wound/Resolve/Stress pips changed and whether the campaign clock moved ONCE (not x party size).

## Portrait Bank 2026-08-03
Item | Status | Description / what to do | Result | Notes
READ FIRST - verifies the portrait-bank private-bucket fix (shipped 2026-08-02, commit 15a8ab2d). Storage-layer mechanism already verified live by Puffer Fish (old public URL 400s, new bucket rejects unsigned access, migrated portrait serves correctly) - this is a 2-minute click-through of the UI path nobody has driven yet as a real logged-in Thriver. Not urgent/blocking.
PART A - Private portrait upload (Create Tokens tool)
1 | TEST | Log in as a Thriver and go to the Create Tokens tool (/tools/token-creator).
2 | TEST | Upload one portrait with the "Private" checkbox checked (single-image mode, gender left unset).
2a | TEST | Does the upload succeed with no error? (yes/no)
3 | TEST | Open character creation's portrait picker (or wherever private portraits are picked from) and look for the portrait you just uploaded.
3a | TEST | Does it show up and display correctly (not broken/blank)? (yes/no)
4 | TEST | (Optional, if easy) Repeat step 2 using Bulk Upload mode with Private checked instead of single-image.
4a | TEST | Same result - uploads fine and shows correctly in the picker? (yes/no) [skip if awkward to set up]
Report back
Fill Pass/Fail + notes and send it back. Not blocking - only insurance against a UI-wiring gap the storage-layer proof can't see.

## Onboarding Tour 2026-08-04
Item | Status | Do this | What you saw | Notes
READ FIRST - this is localhost only (dev server, not live). Hunt & Peck is holding these changes uncommitted until you've seen them - nothing ships until you weigh in. Make sure the dev server is running (Start-Tapestry.bat), then work top to bottom.
Onboarding tour - arrow pointer + drag
1 | DO | Go to localhost:3000/welcome. The tour opens automatically.
2 | DO | Click Next through all 6 steps.
3 | DO | On steps 2-5, watch the left sidebar: a red ring + arrow should point at a link - step 2 = the Tapestry logo, 3 = My Survivors, 4 = The Campfire, 5 = The World. Steps 1 and 6 have no arrow (by design).
4 | DO | Grab the modal by the three-dot grip strip at its very top and drag it around the screen.
5 | REPORT | Do the arrows point at the right things? Does the drag feel right? Is the backdrop dimness (a light scrim, not a blackout) about right? Does pointing at the logo for the "Dashboard" step read OK, or should that step drop its arrow?
Report back
Fill in "What you saw" for row 5 (free text, no pass/fail needed) and send it back. HP commits + pushes once you've signed off.

## Localhost 5-item set 2026-09-16
LOCALHOST ONLY - FIVE FEATURES AWAITING YOUR TEST
All five of these are held UNPUSHED on your local dev server (localhost:3000), not the live site, per the local-first policy. Each is on its own branch, so you can approve them individually - "ship 1 and 3, hold the rest" is a fine answer. Verified before this was written: dev server confirmed up and serving; each feature's code confirmed present in the branch it ships from.
BEFORE YOU START
Make sure your local dev server is running (Start-Tapestry.bat) before starting.
Items 1-3 and 5 (Route tool, Eat/Rest/Relax, Dice roller, NPCs Met) can be tested as the GM.
Item 4 (NPC folders) MUST be tested as a PLAYER - use a second browser or a playtester login, not your GM account.
Item 5 (NPCs Met) needs a campaign where the party has actually met at least one NPC (a First Impression rolled) to show anything other than the empty state.
NOT on localhost, and you should not go looking for it: the fog-of-war / shared-scene fix. It needs one new database column added first, and localhost and live share the same database - adding it now would break the table page for everyone. It ships once you okay that column.
MARKING THE PASS / FAIL COLUMN: Pass = it did what the row said. Fail = it did not, and you saw enough to say so. Skipped = you chose not to run it. Incomplete = you COULD NOT run it, because an earlier step blocked it or you could not find what the step names. A step blocked by an earlier failure is Incomplete, not Skipped. Incomplete is not a failure: nothing was proven either way, and it tells Comms to fix the step rather than chase a bug.
# | Pass / Fail | What you do | What you should see if it is right | Notes
1 |  | [ROUTE TOOL] Open a Story you are the GM of, and go to the campaign map. | The map loads normally, as it always has.
2 |  | [ROUTE TOOL] Click the ROUTE button, then click two spots on the map to plan a route between them. | A route line is drawn along the roads between the two points you clicked.
3 |  | [ROUTE TOOL] Find the speed slider and drag it slowly from one end to the other. Read out every label you pass, in order. | The label changes as you drag. Write down the exact labels and order you saw (expected set: Walking, Bike, Horse, Car 22, Car 40, Car 70).
4 |  | [ROUTE TOOL] Click the TRAVEL button. | A yellow dot appears on the route line and moves from the start point toward the destination.
5 |  | [ROUTE TOOL] Watch what the dot does once it reaches the destination, and drag the speed slider while it is still moving. | Report what the dot does at the end (stop, loop back to the start, disappear - whichever it is) and whether dragging the slider mid-travel changes how fast the dot moves.
6 |  | [EAT / REST / RELAX] Open the Campaign Sheet, then click the Eat button. | Something happens on screen (not the old placeholder alert) - report exactly what.
7 |  | [EAT / REST / RELAX] Click the Rest button. | A modal opens with time-length options (Hours / Days / Weeks) and, once you enter at least 8 hours, a Cooling Off checkbox appears. Report what you see and what you are able to set.
8 |  | [EAT / REST / RELAX] Close that modal, then click the Relax button. | The same kind of modal opens, but pre-filled to an 8-hour restful rest with Cooling Off already checked (one click should be enough). Report what appears and how it differs from Rest.
9 |  | [DICE ROLLER] Go to the table and find the message box at the bottom of the feed. Click the dice button immediately to the left of it. | A dice panel opens. Report every die button you see in it.
10 |  | [DICE ROLLER] Click the d20 button. | A new line appears in the chat showing a d20 roll. Report the exact line.
11 |  | [DICE ROLLER] Click the + next to where it says "1 die" twice (to get to 3 dice), then click d6. | A new line appears showing 3d6 rolled together. Report the exact line.
12 |  | [DICE ROLLER] Click the + next to the modifier number (starts at 0) three times, then click d20. | A new line appears showing a d20 roll with a +3 modifier applied. Report the exact line.
13 |  | [DICE ROLLER] Type /r 2d6+3 into the message box and press Enter. | A line appears in the chat showing that roll's result. Report the exact line.
14 |  | [DICE ROLLER] Type /r banana into the message box and press Enter. | This is the important one. It should show an error message INSIDE the dice/chat area and leave what you typed in the box - it should NOT pop up a browser dialog box. Report exactly what you saw, and say plainly whether a popup appeared or not.
15 |  | [NPC FOLDERS] Open the Story at localhost as a PLAYER, not the GM (use a second browser or a playtester login). Go to the NPCs tab. | The NPC list loads with its folders, same as the GM sees, but you are logged in as a player.
16 |  | [NPC FOLDERS] Drag an NPC onto a different folder heading, then drag an NPC onto another NPC inside the same folder. | The NPC moves into the new folder, and reordering within a folder changes the order shown. Report what happened for both drags.
17 |  | [NPC FOLDERS] Refresh the page. | THIS IS THE REAL TEST. The folder and order changes you just made should still be there after the refresh - not jumped back to alphabetical. Report which one happened.
18 |  | [NPCS MET] Open the Campaign Sheet for a campaign where the party has actually met some NPCs (First Impressions rolled at some point). | The Campaign Sheet loads as usual.
19 |  | [NPCS MET] Look at the grid of panels below the row of action buttons. | A panel headed NPCS MET is there. Report what NPCs are listed and the number on the right of each row (e.g. 2/4 = how many of the party met them, out of how many are at the table). If the panel says "Nobody the party has met yet" for a campaign where no First Impression has ever been rolled, that is correct, not a bug.
20 |  | [NPCS MET] Click one of the rows in that panel. | The card for that same NPC opens - report whether it's the one you clicked.
21 |  | [NPCS MET] Think about who you'd expect to see listed. | Report whether anyone you expected is missing. Note: "met" means actually introduced (a First Impression rolled) - an NPC you created but never introduced is not expected to show up, that's correct behavior, not a bug.
IF ANYTHING FAILS
Tell Comms which bracketed section AND which step number failed - e.g. "[DICE ROLLER] step 13" - so it routes to the right fix straight away.